## Risk Register
Project: HealthFirst Care Initiative Project. Risk Register
Risk ID | Risk Description | Risk Category | Likelihood | Impact | Severity | Mitigation Strategy
R1 | Data Breach | Technical Risks | 2 | 3 | 6 | Implement Strong encyption.
R2 | System Downtime | Technical Risks | 2 | 3 | 6 | Regular Maintenance of system
R3 | Stakeholder resist to change | Stakeholder Risks | 2 | 2 | 4 | Conduct awareness session and provide benefits early on
R4 | Limited Stakeholder Involvement | Stakeholder Risks | 1 | 2 | 2 | Conduct Regular Meetings. Prepare stakeholder engagement plan
R5 | Staff Resistance to change | Operational Risks | 2 | 3 | 6 | Conduct Training Sessions. Offer Incentives
R6 | Software Implementation Delay | Operational Risks | 2 | 3 | 6 | Use Agile Methodologies
R7 | Budget Overrun | Operational Risks | 1 | 3 | 3 | Conduct Time to time budget review
R8 | Integration Failure with existing System | Technical Risks | 2 | 3 | 6 | Conduct Phased integration with backup plans
R9 | Unrealistic Stakeholder Expectations | Stakeholder Risks | 2 | 2 | 4 | Set Clear Acceptance Criteria
R10 | Lack of Skillset required by IT Team | Technical Risks | 2 | 3 | 6 | Arrange Necessary Training and externa support
49
Total Risk Score
|  | Risk Category | Likelihood | Impact Risk Rating
|  | Operational risks | 1. Low | 1. Low
|  | Technical risks | 2. Medium | 2. Medium
|  | Stakeholder risks | 3. High | 3. High