## Risk Assessment Matrix
Project:
[5 empty] | Risk ID | Risk Description | Likelihood | Impact | Severity | Risk Level | Mitigation Strategy
[5 empty] | R1 | Data Breach | 2 | 3 | 6 |  | Implement Strong encyption.
[5 empty] | R2 | System Downtime | 2 | 3 | 6 |  | Regular Maintenance of system
[5 empty] | R3 | Stakeholder resist to change | 2 | 2 | 4
[5 empty] | R4 | Limited Stakeholder Involvement | 1 | 2 | 2
[5 empty] | R5 | Staff Resistance to change | 2 | 3 | 6 |  | Conduct Training Sessions. Offer Incentives
[5 empty] | R6 | Software Implementation Delay | 2 | 3 | 6 |  | Use Agile Methodologies
L | 3 |  |  |  | R7 | Budget Overrun | 1 | 3 | 3
I |  |  |  |  | R8 | Integration Failure with existing System | 2 | 3 | 6 |  | Conduct Phased integration with backup plans
K | 2 |  | R3,R9 | R1,R2,R5,R6,R8,R10 | R9 | Unrealistic Stakeholder Expectations | 2 | 2 | 4
L |  |  |  |  | R10 | Lack of Skillset required by IT Team | 2 | 3 | 6 |  | Arrange Necessary Training and externa support
I | 1 |  | R4 | R7 | Scoring
H |  | 1 | 2 | 3 | Watch List Low |  | 1-2
O |  |  |  |  | Watch List Moderate |  | 3-4
O | I M P A C T |  |  |  | Urgent List High |  | 6-9
D